## Sheet3
Task# | Description | Responsible | Completion | Date | Start time | End Time | Time Spent (h) | Cost per hour ($) | Sub-total | Taxes | Total cost | Total time spent (h) | Subtotal | Taxes | Total cost
3000 | Turn the server on and make sure it is working (hardware check / RAID controller) | Elianne | 100% | 2025-01-14 | 10:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75 | 148.25 | 11118.75 | 1667.815 | 12959.065
3001 | Configure Router E1019 | Yuri | 100% | 2025-01-14 | 10:00 | 11:00 | 1 | 75 | 75 | 11.25 | 86.25
3002 | Configure Router C1002 | Tyler | 100% | 2025-01-14 | 10:45 | 11:30 | 0.75 | 75 | 56.25 | 8.4375 | 64.6875
3004 | Configure Internal Switch C1002 | Tyler | 100% | 2025-01-14 | 11:30 | 12:00 | 0.5 | 75 | 37.5 | 5.625 | 43.125 | Total time spent (h) | Subtotal | Taxes | Total cost
3005 | Get Mini PCs (Dell) workstations | Adhelia | 100% | 2025-01-14 | 8:30 | 11:30 | 3 | 75 | 225 | 33.75 | 258.75 | 40.75 | 3056.25 | 458.4375 | 3514.6875
3006 | Install Windows 2011 on a MiniPC | Adhelia | 100% | 2025-01-15 | 13:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3007 | Install Ubuntu 24.04 on a MiniPC | Elianne | 100% | 2025-01-14 | 8:30 | 10:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3008 | Create a Physical Diagram (basic understanding) | Elianne | 100% | 2025-01-21 | 13:30 | 14:30 | 1 | 75 | 75 | 11.25 | 258.75
3009 | Create a Logical Diagram (basic understanding) | Adhelia | 100% | 2025-01-21 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3009 | Create a Logical Diagram (basic understanding) - continuation | Adhelia | 100% | 2025-01-21 | 13:30 | 15:30 | 3 | 75 | 225 | 33.75 | 258.75
3010 | Create documentation for tasks/bill | Yuri | 100% | 2025-01-14 | 10:00 | 11:00 | 1 | 75 | 75 | 11.25 | 86.25
3011 | Initial Meeting to define tasks | All members | 100% |  | 8:30 | 9:30 | 1 | 75 | 75 | 11.25 | 86.25
3012 | Configure Cyclades Box | Tyler | 100% | 2025-01-14 | 9:45 | 10:30 | 0.75 | 75 | 56.25 | 8.44 | 64.69
3013 | Bring routers to E1019 and erase startup config | Yuri | 100% | 2025-01-08 | 10:00 | 11:00 | 1 | 75 | 75 | 11.25 | 86.25
3014 | Add new configuration to router in C1002 (internal Router) | Tyler | 100% | 2025-01-21 | 9:00 | 10:00 | 1 | 75 | 75 | 11.25 | 86.25
3015 | Add new configuration to router in E1019 (external Router) | Yuri | 100% | 2025-01-21 | 9:00 | 10:00 | 1 | 75 | 75 | 11.25 | 86.25
3017 | Install tftp server for conf backup on Windows server and backup routers | Yuri / Tyler | 100% | 2025-01-22 | 9:00 | 10:00 | 1 | 75 | 75 | 11.25 | 86.25
3018 | Install Windows 2022 on Server and configure ip address and password | Elianne | 100% | 2055-01-22 | 11:00 | 12:30 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3019 | Creating automatic backup configuration for Internal and External routers | Yuri | 100% | 2025-01-28 | 9:00 | 10:30 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3020 | Map all ports and devices through show cdp neighbors | Yuri | 100% | 2025-01-29 | 9:00 | 10:30 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3021 | Updated routing tables on External Router. Configured VLANs/trunk on Switches | Yuri | 100% | 2025-01-29 | 13:30 | 15:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3022 | Research how do make a cron job to backup the routers | Tyler | 100% | 2025-01-28 | 9:00 | 10:00 | 1 | 75 | 75 | 11.25 | 86.25
3023 | Install ad configure windows server 2022 on our physical server | Elianne | 100% | 2025-01-14 | 8:30 | 10:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3024 | Configuring the server again after finding hardware issues. | Elianne | 100% | 2025-01-15 | 13:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3025 | Draw the Physical diagram topology for our network (include devices) | Elianne | 100% | 2025-01-21 | 13:30 | 14:30 | 1 | 75 | 75 | 11.25 | 86.25
3026 | Reinstalling hardware parts on the server | Elianne | 100% | 2025-01-28 | 8:30 | 10:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3027 | Conclusion of the physical diagram (include VLANs, Ports, ip addresses) | Elianne | 100% | 2025-01-29 | 13:30 | 14:30 | 1 | 75 | 75 | 11.25 | 86.25
3028 | Verifying cable connections of mini PCs and wall jacks | Adhelia | 100% | 2025-01-28 | 9:30 | 10:30 | 1 | 75 | 75 | 11.25 | 86.25
3029 | Configure ntp server on external router | Yuri | 100% | 2025-02-04 | 9:30 | 10:30 | 1 | 75 | 75 | 11.25 | 86.25
3030 | Configure new routing table on internal router | Yuri | 100% | 2025-02-04 | 10:30 | 12:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3031 | Meeting to define project 2 task | All members | 100% | 2025-02-04 | 9:00 | 9:30 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3032 | Create VMs on R7S6 | Adhelia | 100% | 2025-02-04 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3033 | Help figure out the system problems with Win 11 VM | Elianne/Tyler | 100% | 2025-02-04 | 9:45 | 11:00 | 1.25 | 75 | 93.75 | 14.0625 | 107.8125
3034 | Configure the child domain on R7S6 | Elianne | 100% | 2025-02-12 | 1:30 | 2:30 | 1 | 75 | 75 | 11.25 | 86.25
3035 | Configure the backup domain controller on R7S8 | Tyler | 100% | 2025-02-12 | 10:30 | 12:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3036 | Configure virtual clients on R7S6 | Adhelia | 100% | 2025-02-04 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3037 | Configure Windows virtual client on R7S8 | Tyler | 100% | 2025-02-05 | 13:30 | 14:00 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3038 | Configure Linux virtual client on R7S8 | Elianne | 100% | 2025-02-05 | 13:30 | 14:00 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3039 | Configure ACLs on Internal Router | Yuri | 100% | 2025-02-04 | 13:30 | 15:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3040 | [8 empty] | 0 | 0 | 0
3041 | Go over checklist for VM's on R7S8 | Tyler | 100% | 2025-02-12 | 14:00 | 15:00 | 1 | 75 | 75 | 11.25 | 86.25
3042 | Go over checklist for VM's on R7S6 | Elianne | 100% | 2025-02-12 | 13:30 | 14:00 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3043 | Go over checklist for Physical Clients | Adhelia | 100% | 2025-02-11 | 13:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3044 | Reconfigure ACLs on Internal Router | Yuri | 100% | 2025-02-11 | 10:00 | 11:30 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3045 | Configure NAT/PAT on External Router | Yuri | 100% | 2025-02-12 | 11:30 | 13:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3046 | Configure NTP on internal router / Review automatic backup configuration / review routing table | Yuri | 100% | 2025-02-12 | 13:30 | 15:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3047 | Configure DHCP and create dns forwader | Elianne | 100% | 2025-02-18 | 8:30 | 9:30 | 1 | 75 | 75 | 11.25 | 86.25
3048 | Add the provided users and create the OU's | Elianne |  | 2025-02-18 |  |  |  |  | 0 | 0 | 0
3049 | Create Shared Folders for the OU's and limit access to only allow access to the respictive OU's | Tyler | 100% | 2025-02-18 | 10:00 | 11:00 | 1 | 75 | 75 | 11.25 | 86.25
3050 | Create a GPO to map a drive the respective shares using :U | Tyler | 100% | 2025-02-18 | 11:00 | 12:00 | 1 | 75 | 75 | 11.25 | 86.25
3051 | Create 4 Groups matching the OU's, add 4 users to each, make 4 directories for each group for linux | Adhelia | 100% | 2025-02-18 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3052 | Create 4 Groups matching the OU's, add 4 users to each, make 4 directories for each group for the linux VM's | Adhelia | 100% | 2025-02-19 | 1:30 | 3:30 | 2 | 75 | 150 | 22.5 | 172.5
3053 | Help add the provided users | Tyler | 100% | 2025-02-20 | 20:00 | 22:00 | 2 | 75 | 150 | 22.5 | 172.5
3054 | Configure new External Router and HSRP | Yuri | 100% | 2025-02-18 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3055 | Draw Network Diagram and AD Diagram | Yuri | 100% | 2025-02-19 | 13:30 | 17:30 | 4 | 75 | 300 | 45 | 345
3056 | Connect Linux client to domain | Elianne | 100% | 2025-02-18 | 13:30 | 2:00 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3057 | Logon on Users in different OU | [7 empty] | 0 | 0 | 0
3058 | Creating password and Account policy | [7 empty] | 0 | 0 | 0
3059 | Creating LampServer and getting server Configuration | [7 empty] | 0 | 0 | 0
3060 | Meeting to define project 3 tsak | All members | 100% | 04-03-2025 | 9am | 9:30am | 0.5 | 75 | 37.5 | 5.625 | 43.125
3061 | Web page | Elianne/Tyler |  | 04-03-2025 |  |  |  |  | 0 | 0 | 0
3062 | TFTP Server | Yuri |  | 04-03-2025 |  |  |  |  | 0 | 0 | 0
3063 | Linux syslog | Adhelia | 100% | 2025-04-03 | 10AM | 12:30 | 2.5 | 75 | 187.5 | 28.125 | 215.625
3064 | Configure Multilayer switch for C1002 | Tyler | 100% | 2025-04-03 | 10:00 | 12:30 | 2.5 | 75 | 187.5 | 28.125 | 215.625
3065 | Configure Multilayer switch for C1002 | Tyler | 100% | 2025-04-03 | 1:30 | 3:30 | 2 | 75 | 150 | 22.5 | 172.5
3066 | Deleting NAT From on Our Internal Router | Elianne | 100% | 2025-04-03 | 9:30 | 10:30 | 1 | 75 | 75 | 11.25 | 86.25
3067 | Recreating Linux Vm and getting it connected to domain | Elianne | 100% | 2025-04-03 | 11:00 | 11:30 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3068 | Creating policy for technicians wallpaper | Elianne | 100% | 2025-04-03 | 13:30 | 15:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3069 | Verifying that all host virtual and physical boxes are pointing to the correct DNS server | Adhelia | 100% | 2025-04-03 | 10:00 | 12:30 | 2.5 | 75 | 187.5 | 28.125 | 215.625
3070 | Configure tftp server on Linux VM | Yuri | 100% | 2025-03-11 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3071 | Create a bash script to rename files to append date and time | Yuri | 100% | 2025-03-12 | 13:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3072 | Implement MLS into network in room C1002 | Tyler | 100% | 2025-03-11 | 9:00 | 12:00 | 3 | 75 | 225 | 33.75 | 258.75
3073 | Test HSRP on the router in C1002 | Tyler | 100% | 2025-03-12 | 13:45 | 14:00 | 0.25 | 75 | 18.75 | 2.8125 | 21.5625
3074 | Configure the wireless access point using web GUI | Tyler |  | 2025-03-12 | 14:15 | 3:30 | 1.25 | 75 | 93.75 | 14.0625 | 107.8125
3075 | Configuring Lamp server (Webpage) | Elianne | 100% | 2025-03-14 | 8:00 | 13:00 | 5 | 75 | 375 | 56.25 | 431.25
3076 | Get a POE+ switch from the cybersecurity storage room | Tyler | 100% | 2025-03-18 | 9:00 | 9:30 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3077 | Configure the wireless access point using CLI | Tyler | 90% | 2025-03-18 | 9:30 | 10:30 | 1 | 75 | 75 | 11.25 | 86.25
3078 | Configure POE+ switch that will supply power to all teams AP's through the wall ports | Tyler | 100% | 2025-03-19 | 13:45 | 14:00 | 0.25 | 75 | 18.75 | 2.8125 | 21.5625
3079 | Verify that the AP is configure correctly | Tyler | 100% | 2025-03-19 | 14:15 | 15:30 | 1.25 | 75 | 93.75 | 14.0625 | 107.8125
3080 | Troubleshoot VLAN 133 - No connectivity for the Lamp server | Yuri | 100% | 2025-03-18 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3081 | Reconfigure and troubleshoot NAT | Yuri /Elianne | 100% | 2025-03-19 | 13:30 | 16:30 | 3 | 75 | 225 | 33.75 | 258.75
3082 | Installing Radius Server on DC1 | Yuri | 100% | 2025-03-20 | 9:00 | 11:00 | 2 | 75 | 150 | 22.5 | 172.5
3083 | Troubleshooting DNS and the access to the t3webpage. | Yuri | 100% | 2025-03-20 | 11:00 | 12:00 | 1 | 75 | 75 | 11.25 | 86.25
3084 | Creation of DNS Forward Lookup Zone and Reverse lookup zone | Elianne | 100% | 2025-03-20 | 9:00 | 10:00 | 1 | 75 | 75 | 11.25 | 86.25
3085 | Permitting pinging between our domain and Physical server | Elianne | 100% | 2025-03-20 | 10:00 | 11:00 | 1 | 75 | 75 | 11.25 | 86.25
3086 | Testing Configuration and website | Elianne | 100% | 2025-03-20 | 11:00 | 12:00 | 1 | 75 | 75 | 11.25 | 86.25
3087 | Troubleshooting AP and network connectivity with AP | Yuri/Tyler | 100% | 2025-03-25 | 9:30 | 12:30 | 3 | 75 | 225 | 33.75 | 258.75
3088 | Trobleshooting Radius Server on DC1 | Yuri/Tyler | 80% | 2025-03-26 | 13:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3089 | Reconfigure and troubleshoot TFTP and Syslog server | Elianne | 100% | 2025-03-26 | 14:30 | 16:30 | 2 | 75 | 150 | 22.5 | 172.5
3090 | Reconfigure the Access Point to the new Specifications | Tyler | 100% | 2025-04-01 | 9:00 | 12:00 | 3 | 75 | 225 | 33.75 | 258.75
3091 | Configure the new Access Point | Tyler | 100% | 2025-04-02 | 2:00 | 2:30 | 0.5 | 75 | 37.5 | 5.625 | 43.125
3092 | Creating new security group for shared folder in between different teams | Yuri | 100 | 2025-04-01 | 10:00 | 11:30 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3093 | Troubleshooting Linux and Windows boxes for network connectivity | Yuri | 100 | 2025-04-02 | 13:30 | 15:00 | 1.5 | 75 | 112.5 | 16.875 | 129.375
3094 | Configuring replacment router | Tyler/Yuri | 100% | 2025-04-08 | 9:00 | 12:30 | 3.5 | 75 | 262.5 | 39.375 | 301.875
3095 | Continuing configuration of replacment router | Tyler/Yuri | 100% | 2025-04-09 | 1:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3096 | Working on windows checklist as student 1 | Elianne | 100% | 2025-04-09 | 1:30 | 15:30 | 2 | 75 | 150 | 22.5 | 172.5
3097 | Completing creation of share folder | Elianne | 100% | 2025-04-08 | 9:00 | 12:30 | 84:00 | 75 | 262.5 | 39.375 | 301.875
[9 empty] | 0 | 0 | 0

## Yuri
Task# | Description | Responsible | Completion | Date | Start time | End Time | Time Spent (h) | Cost per hour ($) | Sub-total | Taxes | Total cost | Total time spent (h) | Subtotal | Taxes | Total cost
3094 | Configuring replacment router | Tyler/Yuri | 100% | 2025-04-08 | 9:00 | 12:30 | 3.5 | 75 | 262.5 | 39.375 | 301.875 | 5.5 | 412.5 | 61.875 | 474.375
3095 | Continuing the configuration of replacement router | Tyler/Yuri | 100% | 2025-04-09 | 1:30 | 3:30 | 2 | 75 | 150 | 22.5 | 172.5
3074
3075
3074
3075
3076
3077
3078
3079 | `